## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Overview
| Table 1 | Overview
Execution Log
| Table 1 | Execution Log
Dashboard
| Table 1 | Dashboard
Environment
| Table 1 | Environment
Defect Candidates
| Table 1 | Defect Candidates

## Overview
SAUCEDEMO - TEST EXECUTION
Document ID | QA-TE-001
Version | 1.0
Prepared By | Nancy McKenzie
Application | SauceDemo
Project | Manual QA Testing Portfolio
Related Test Plan | QA-TP-001
Related Requirements | QA-BRD-001
Related Scenarios | QA-TS-001
Related Test Cases | QA-TC-001
Purpose
This workbook is the execution control for the 42 detailed SauceDemo test cases. It is designed to capture actual results, Pass/Fail/Blocked status, execution date, tester, evidence references, and defect linkage. The workbook intentionally starts with all cases marked Not Run so that the final portfolio reflects real execution evidence rather than invented results.
Execution Standard | How It Is Applied | Why It Matters | Portfolio Value
Actual Evidence | Results are entered only after a real execution attempt. | Protects credibility. | Demonstrates honest QA practice.
Defect Linkage | Failed cases reference a defect candidate or defect ID. | Connects testing to defect management. | Shows full QA lifecycle.
Repeatability | Expected result and source test-case IDs remain visible. | Makes retesting easier. | Supports professional regression work.
Status Control | Only Not Run, Pass, Fail, Blocked, or N/A are allowed. | Keeps metrics clean. | Enables reliable reporting.
Dashboard Metrics | Counts and rates update from the Execution Log. | Makes progress visible. | Creates recruiter-friendly summary.

## Execution Log
Execution ID | Test Case ID | Scenario ID | Requirement ID(s) | Module | Test Case Title | Priority | Expected Result | Actual Result | Status | Defect ID | Evidence / Screenshot | Executed By | Execution Date | Retest Status | Retest Date | Notes
EXE-001 | TC-001 | TS-001 | REQ-001 | Authentication | Login with valid standard user | Critical | Login succeeds and Inventory page is displayed. | Login successfully. Inventory pages displays available products. | Pass |  |  | Nancy Mckenzie | 2026-08-16 | Not Required
EXE-002 | TC-002 | TS-002 | REQ-002 | Authentication | Reject invalid username | Critical | Login is rejected and a clear error message is displayed. | Login was rejected. Error message was displayed. | Pass |  |  | Nancy Mckenzie | 2026-08-16 | Not Required
EXE-003 | TC-003 | TS-003 | REQ-002 | Authentication | Reject invalid password | Critical | Login is rejected and an authentication error is displayed. | Login was rejected . An authentication error was displayed. | Pass |  |  | Nancy Mckenzie | 2026-08-16 | Not Required
EXE-004 | TC-004 | TS-003 | REQ-002 | Authentication | Validate blank username | Critical | Login does not proceed and required username validation is displayed. | Login does not proceed . Required username validation message is displayed. | Pass |  |  | Nancy Mckenzie | 2026-08-16 | Not Required
EXE-005 | TC-005 | TS-003 | REQ-002 | Authentication | Validate blank password | Critical | Login does not proceed and required password validation is displayed. | Login does not proceed. Required password validation was displayed. | Pass |  |  | Nancy Mckenzie | 2026-08-16 | Not Required
EXE-006 | TC-006 | TS-004 | REQ-003 | Authentication | Reject locked-out user | Critical | User remains unauthenticated and locked-out error message is shown. | User remains unauthenticated. Locked-out error message is shown. | Pass |  |  | Nancy Mckenzie | 2026-08-16 | Not Required
EXE-007 | TC-007 | TS-005 | REQ-004, REQ-005 | Inventory | Display inventory after valid login | Critical | Inventory page loads and available product cards are visible. | Inventory page loads. Available product cards are visible. | Pass |  |  | Nancy Mckenzie | 2026-08-16 | Not Required
EXE-008 | TC-008 | TS-005 | REQ-005 | Inventory | Validate product information on inventory | High | Each product displays readable identifying information and price. | Each product displays readable identifying information and price. | Pass |  |  | Nancy Mckenzie | 2026-08-16 | Not Required
EXE-009 | TC-009 | TS-006 | REQ-006 | Inventory | Sort products name A to Z | High | Products appear in ascending alphabetical order. | Products appear in ascending alphabetical order. | Pass |  |  |  |  | Not Required
EXE-010 | TC-010 | TS-006 | REQ-006 | Inventory | Sort products name Z to A | High | Products appear in descending alphabetical order. | Products appear in descending alphabetical order. | Pass |  |  |  |  | Not Required
EXE-011 | TC-011 | TS-006 | REQ-006 | Inventory | Sort products price low to high | High | Products are ordered from lowest to highest price. | Products are ordered from lowest to highest price. | Pass |  |  |  |  | Not Required
EXE-012 | TC-012 | TS-006 | REQ-006 | Inventory | Sort products price high to low | High | Products are ordered from highest to lowest price. | Products are ordered from highest to lowest price. | Pass |  |  |  |  | Not Required
EXE-013 | TC-013 | TS-007 | REQ-007 | Product Details | Open product details from product name | Medium | Correct product detail page opens with matching product information. | Correct product detail page opens with matching product information. | Pass |  |  |  |  | Not Required
EXE-014 | TC-014 | TS-007 | REQ-007 | Product Details | Return from product details to inventory | Medium | Inventory page is displayed again. | Inventory page is displayed again. | Pass |  |  |  |  | Not Required
EXE-015 | TC-015 | TS-008 | REQ-008 | Cart | Add one product from inventory | Critical | Product is selected and cart badge shows 1. | Product is selected and cart badge shows 1. | Pass |  |  |  |  | Not Required
EXE-016 | TC-016 | TS-008 | REQ-008 | Cart | Add product from detail page | High | Product is added and cart badge shows 1. | Product is added and cart badge shows 1. | Pass |  |  |  |  | Not Required
EXE-017 | TC-017 | TS-009 | REQ-008, REQ-010 | Cart | Add multiple products | Critical | Both selected products are present in the cart. | Both selected products are present in the cart. | Pass |  |  |  |  | Not Required
EXE-018 | TC-018 | TS-011 | REQ-010, BRULE-03 | Cart | Validate cart badge after multiple additions | High | Badge count accurately tracks the number of selected items. | Badge count accurately tracks the number of selected items. | Pass |  |  |  |  | Not Required
EXE-019 | TC-019 | TS-010 | REQ-009 | Cart | Remove product from inventory selection | Critical | Product is deselected and cart badge updates accordingly. | Product is deselected and cart badge updates accordingly. | Pass |  |  |  |  | Not Required
EXE-020 | TC-020 | TS-010 | REQ-009 | Cart | Remove product from cart page | Critical | Product is removed from cart and badge count updates. | Product is removed from cart and badge count updates. | Pass |  |  |  |  | Not Required
EXE-021 | TC-021 | TS-010, TS-011 | REQ-009, REQ-010 | Cart | Validate cart state after removing one of multiple products | Critical | Only the intended item is removed; remaining item stays and badge shows 1. | Only the intended item is removed; remaining item stays and badge shows 1. | Pass |  |  |  |  | Not Required
EXE-022 | TC-022 | TS-012 | REQ-011 | Cart | Continue shopping preserves cart | Medium | Inventory reopens and previously selected product remains in cart. | Inventory reopens and previously selected product remains in cart. | Pass |  |  |  |  | Not Required
EXE-023 | TC-023 | TS-009 | REQ-010 | Cart | Validate cart item details | High | Cart displays the correct selected product and matching price. | Cart displays the correct selected product and matching price. | Pass |  |  |  |  | Not Required
EXE-024 | TC-024 | TS-013 | REQ-012 | Checkout | Start checkout with item in cart | Critical | Checkout: Your Information page opens. | Checkout: Your Information page opens. | Pass |  |  |  |  | Not Required
EXE-025 | TC-025 | TS-014 | REQ-013 | Checkout | Require first name | Critical | Checkout does not advance and first-name required error is displayed. | Checkout does not advance and first-name required error is displayed. | Pass |  |  |  |  | Not Required
EXE-026 | TC-026 | TS-015 | REQ-013 | Checkout | Require last name | Critical | Checkout does not advance and last-name required error is displayed. | Checkout does not advance and last-name required error is displayed. | Pass |  |  |  |  | Not Required
EXE-027 | TC-027 | TS-016 | REQ-013 | Checkout | Require postal code | Critical | Checkout does not advance and postal-code required error is displayed. | Checkout does not advance and postal-code required error is displayed. | Pass |  |  |  |  | Not Required
EXE-028 | TC-028 | TS-017 | REQ-013, REQ-014 | Checkout | Continue checkout with valid customer information | Critical | Checkout Overview page opens and cart items are retained. | Checkout Overview page opens and cart items are retained. | Pass |  |  |  |  | Not Required
EXE-029 | TC-029 | TS-018 | REQ-014 | Checkout | Validate order overview product details | Critical | Overview accurately reflects selected cart item details. | Overview accurately reflects selected cart item details. | Pass |  |  |  |  | Not Required
EXE-030 | TC-030 | TS-019 | REQ-015 | Checkout | Validate order subtotal | Critical | Displayed item subtotal equals the sum of selected item prices. | Displayed item subtotal equals the sum of selected item prices. | Pass |  |  |  |  | Not Required
EXE-031 | TC-031 | TS-019 | REQ-015 | Checkout | Validate tax and total consistency | Critical | Displayed Total equals Item total plus Tax. | Displayed Total equals Item total plus Tax. | Pass |  |  |  |  | Not Required
EXE-032 | TC-032 | TS-020 | REQ-016 | Order Completion | Complete a valid single-item order | Critical | Order completes and success confirmation is displayed. | Order completes and success confirmation is displayed. | Pass |  |  |  |  | Not Required
EXE-033 | TC-033 | TS-020 | REQ-016 | Order Completion | Complete a valid multi-item order | Critical | Order completes successfully and confirmation is displayed. | Order completes successfully and confirmation is displayed. | Pass |  |  |  |  | Not Required
EXE-034 | TC-034 | TS-020 | REQ-016 | Order Completion | Return to inventory after order completion | Medium | Inventory page opens successfully. | Inventory page opens successfully. | Pass |  |  |  |  | Not Required
EXE-035 | TC-035 | TS-021 | REQ-017 | Navigation | Open and close application menu | High | Menu opens and closes without corrupting page state. | Menu opens and closes without corrupting page state. | Pass |  |  |  |  | Not Required
EXE-036 | TC-036 | TS-021 | REQ-017 | Navigation | Use All Items menu action | High | Inventory page is displayed. | Inventory page is displayed. | Pass |  |  |  |  | Not Required
EXE-037 | TC-037 | TS-021 | REQ-017 | Navigation | Use Reset App State | High | Application state is reset according to demo behavior and shopping state is cleared. | Application state is reset according to demo behavior and shopping state is cleared. | Pass |  |  |  |  | Not Required
EXE-038 | TC-038 | TS-022 | REQ-018, BRULE-08 | Session | Logout authenticated user | High | User returns to login page and authenticated session ends. | User returns to login page and authenticated session ends. | Pass |  |  |  |  | Not Required
EXE-039 | TC-039 | TS-022 | REQ-018, NFR-006 | Session | Verify normal authenticated navigation is unavailable after logout | High | Inventory is not accessible through normal UI flow until valid login occurs. | Inventory is not accessible through normal UI flow until valid login occurs. | Pass |  |  |  |  | Not Required
EXE-040 | TC-040 | TS-023 | NFR-001, NFR-003 | Usability & UI | Validate clarity of login and checkout validation messages | High | Messages are visible, readable, and indicate the problem clearly enough for corrective action. | Combined usability validation covering both login error messaging and checkout required-field validation. Both messages were reviewed for visibility, readability, and clarity. | Pass |  |  |  |  | Not Required
EXE-041 | TC-041 | TS-023 | NFR-004 | Usability & UI | Validate readability and association of product information | High | Product information is readable and consistently associated with the correct item. | Product image doesn’t match the description of the product. | Fail |  |  |  |  | Not Required
EXE-042 | TC-042 | TS-024 | REQ-001, REQ-004, REQ-008, REQ-012, REQ-013, REQ-014, REQ-015, REQ-016, NFR-002, NFR-006 | End-to-End | Execute complete standard purchase journey | Critical | User completes the full purchase path with consistent cart state, valid checkout data, accurate overview, and successful confirmation. | User completes the full purchase path with consistent cart state, valid checkout data, accurate overview, and successful confirmation. | Pass |  |  |  |  | Not Required

## Dashboard
TEST EXECUTION DASHBOARD
Metric | Value | Module | Total | Pass | Fail
Total Test Cases | 42 | Authentication | 6 | 6 | 0
Executed | 42 | Inventory | 6 | 6 | 0
Pass | 41 | Product Details | 2 | 2 | 0
Fail | 1 | Cart | 9 | 9 | 0
Blocked | 0 | Checkout | 8 | 8 | 0
Not Run | 0 | Order Completion | 3 | 3 | 0
Execution % | 100% | Navigation | 3 | 3 | 0
Pass Rate % | 97.62% | Session | 2 | 2 | 0
|  | Usability & UI | 2 | 1 | 1
|  | End-to-End | 1 | 1 | 0
Execution Guidance
Use the Execution Log during actual SauceDemo testing. For each test case, enter the observed Actual Result, select a Status, record the tester and execution date, and add a screenshot/evidence reference when helpful. If a case fails, create a Defect Candidate and link its ID back to the execution row. The dashboard will then calculate execution progress and outcome metrics automatically.

## Environment
TEST EXECUTION ENVIRONMENT
Application URL | https://www.saucedemo.com/
Application | SauceDemo
Testing Method | Manual Functional Testing
Primary Browser | Google Chrome
Operating System | macOS / Windows 11
Test Account | standard_user
Locked Account | locked_out_user
Password | secret_sauce
Execution Evidence | Screenshots / notes / defect references

## Defect Candidates
Candidate ID | Test Case ID | Module | Summary | Observed Result | Expected Result | Severity | Priority | Status | Evidence | Created By | Created Date | Notes
DC-001 | [7 empty] | New
DC-002 | [7 empty] | New
DC-003 | [7 empty] | New
DC-004 | [7 empty] | New
DC-005 | [7 empty] | New
DC-006 | [7 empty] | New
DC-007 | [7 empty] | New
DC-008 | [7 empty] | New
DC-009 | [7 empty] | New
DC-010 | [7 empty] | New
DC-011 | [7 empty] | New
DC-012 | [7 empty] | New
DC-013 | [7 empty] | New
DC-014 | [7 empty] | New
DC-015 | [7 empty] | New