## Overview
SAUCEDEMO - DEFECT MANAGEMENT
Document ID | QA-DM-001
Version | 2.0 - Consolidated Final
Application Under Test | SauceDemo / Swag Labs
Project | Manual QA Testing Portfolio
Prepared By | Nancy McKenzie
Primary Test Case | TC-041
Scenario | TS-023
Requirement | NFR-004
Confirmed Defects | 3
Purpose
This is the final consolidated defect-management artifact for the SauceDemo Manual QA portfolio. It combines the defect-management framework with the three defects confirmed during execution of TC-041. Each defect is tracked separately so it can be independently reviewed, fixed, retested, and closed.

## Defect Log
Defect ID | Test Case ID | Scenario ID | Requirement ID(s) | Module | Defect Summary | Description / Observed Result | Steps to Reproduce | Expected Result | Severity | Priority | Status | Environment | Evidence | Reported By | Reported Date | Assigned To | Retest Result | Closed Date | Notes
BUG-001 | TC-041 | TS-023 | NFR-004 | Product Information / UI | Product image inconsistent with Test.allTheThings() T-Shirt (Red) information | The product is identified and described as a red T-shirt; however, the displayed image appears to show an orange long-sleeved sweatshirt/sweater-style garment. | 1. Log in with standard_user. 2. Navigate to Products. 3. Locate Test.allTheThings() T-Shirt (Red). 4. Compare name/description with the image. | The product image should be consistent with the advertised product type and color described in the product information. | Medium | P3 | New | SauceDemo / Google Chrome | BUG-001_Product_Image_Information_Mismatch.png | Nancy McKenzie | 08/16/2026 |  | Not Retested |  | Product image appears inconsistent with both the advertised product type and color.
BUG-002 | TC-041 | TS-023 | NFR-004 | Product Information / UI | Red bolt graphic missing from Sauce Labs Bolt T-Shirt image | The product description states that the Sauce Labs Bolt T-Shirt is heather gray with a red bolt; however, the displayed product image does not show the described red bolt design. | 1. Log in with standard_user. 2. Navigate to Products. 3. Locate Sauce Labs Bolt T-Shirt. 4. Compare the description with the image. | The product image should visually match the description, including the stated red bolt design. | Medium | P3 | New | SauceDemo / Google Chrome | BUG-002_Bolt_TShirt_Missing_Red_Bolt.png | Nancy McKenzie | 08/16/2026 |  | Not Retested |  | Missing red bolt is an objective image/description inconsistency.
BUG-003 | TC-041 | TS-023 | NFR-004 | Product Information / UI | Sauce Labs Onesie image does not match stated 3-snap closure | The product description states that the Sauce Labs Onesie has a reinforced 3-snap bottom closure; however, the displayed product image visibly shows only two bottom snaps. | 1. Log in with standard_user. 2. Navigate to Products. 3. Locate Sauce Labs Onesie. 4. Compare description with the image. 5. Count visible bottom snaps. | The product image should accurately reflect the stated three-snap bottom closure. | Medium | P3 | New | SauceDemo / Google Chrome | BUG-003_Onesie_Snap_Closure_Mismatch.png | Nancy McKenzie | 08/16/2026 |  | Not Retested |  | Separate defect because it affects a different product and can be fixed/retested independently.

## Defect Workflow
DEFECT WORKFLOW
Step | Status | Meaning | QA Action | Typical Next Status
1 | New | Defect has been logged. | Document evidence and impact. | Confirmed / Rejected
2 | Confirmed | Issue has been validated as a defect. | Provide complete reproduction details. | In Progress
3 | In Progress | Fix is being worked on. | Remain available for clarification. | Fixed
4 | Fixed | Developer reports issue corrected. | Prepare for retest. | Ready for Retest
5 | Ready for Retest | Fix is available to QA. | Re-execute failed case and related regression. | Closed / In Progress
6 | Closed | Retest passed and defect is resolved. | Record retest result and closure date. | -
7 | Rejected | Issue is not accepted as a defect. | Document rationale. | -

## Severity Priority
SEVERITY & PRIORITY DEFINITIONS
Severity | Definition | Example | Typical Treatment
Critical | Core workflow unusable with no workaround. | Valid users cannot log in or checkout cannot be completed by anyone. | Immediate / release blocking
High | Major functional failure or materially incorrect business behavior. | Cart loses products or order total is incorrect. | Fix before release where feasible
Medium | Incorrect behavior/content affects quality but does not block core flow. | Product image does not match product description. | Schedule correction and retest
Low | Minor cosmetic/content problem with little user impact. | Small alignment or non-blocking copy issue. | Backlog / capacity based
Priority | Definition | Typical Use | Common Severity Relationship
P1 | Immediate fix required. | Release blocker / urgent risk. | Often Critical
P2 | Fix in current cycle. | Major customer or business impact. | Often High
P3 | Important but schedulable. | Moderate impact; core workflow remains available. | Often Medium
P4 | Low urgency. | Minor issue / backlog candidate. | Often Low

## Dashboard
DEFECT DASHBOARD
Metric | Count | Priority | Count
Total Confirmed Defects | 3 | P1 | 0
Critical | 0 | P2 | 0
High | 0 | P3 | 3
Medium | 3
Low | 0
Open / New | 3

## Evidence Index
DEFECT EVIDENCE INDEX
Defect ID | Evidence Filename | What the Screenshot Shows | Captured By | Date | Portfolio Use
BUG-001 | BUG-001_Product_Image_Information_Mismatch.png | T-Shirt (Red) information compared with an image that appears to show an orange long-sleeved garment. | Nancy McKenzie | 08/16/2026 | Store screenshot with defect-management evidence.
BUG-002 | BUG-002_Bolt_TShirt_Missing_Red_Bolt.png | Bolt T-Shirt description references a red bolt while the displayed image does not visibly show one. | Nancy McKenzie | 08/16/2026 | Store screenshot with defect-management evidence.
BUG-003 | BUG-003_Onesie_Snap_Closure_Mismatch.png | Onesie description states a 3-snap closure while only two snaps are visible in the image. | Nancy McKenzie | 08/16/2026 | Store screenshot with defect-management evidence.